Title: ***Digital Powered Teaching (D.P.T.)***

**2023-1-RO01-KA220-SCH-000151960**

**The Partnership Implementation Plan**

| **Objectives (O)** | **WP** | **Resources required (human/financial)** | **Responsible** | **Deadline for completion** | **Expected results** | **Indicators** |
| --- | --- | --- | --- | --- | --- | --- |
| **O1, O2, O3** | **PM** | **24 000 euros** |  |  |  |  |
| Drawing up and signing bilateral partnership agreements, transferring the budget to each partner | PM | - the partnership budget = 80% from total grant allocated (96000 euro)  - the ***Financial Committee*** (FC) from each school | RO | Oct. 2023 | 4 partnership agreements  (RO,HR,CY,EL) | -receiving 80% of the grant allocated by each partner  -financial report will be made quarterly by FC |
| Establishment of the ***Steering Committee*** (SC) of the project | PM | project coordinators RO,HR,CY,EL | RO | Oct. 2023 | Organisation, monitoring and evaluation of all activities | -respect of deadlines and quality of activities  - online monthly meetings |
| Setting up management teams | PM | - 5 persons from each school | SC | 30 oct. 2023 | 4 management teams | Selection criteria |
| Selection of students and teachers in the project implementation teams | PM | -18 students,  - 8 teachers | SC | 30 nov. 2023 | 4 students teams  4 teachers teams | Selection criteria and procedures for students and teachers |
| Realisation the project implementation plan | PM | - project coordinators | Romania | Nov. 2023 | 4forms delivered | 1 interim report, 1 final report |
| Realisation the plan for cooperation and communication | PM | 4 members of management teams | SC | Nov. 2023 | 1 plan, posts on eTwinning site of project | Using different channel for efficient communication |
| Realisation the plan for monitoring and evaluation project results | PM | -project coordinators | SC | Dec. 2023 | 1 plan, tools for monitoring and evaluation | Achieving the objectives of the partnership at a high quality level |
| Realisation the plan for dissemination and exploitation the project results | PM | - project coordinators | Cyprus | Dec.2023 | 1 plan, promoting the project | - are established in WP4 |
| **O1, O2, O3** | **WP2** | **84 720,00 euros** |  |  |  |  |
| O1, O2, O3  Short-term exchange for group of students – teaching and learning activities in *arts and technologies* | WP2 | - 18 students (RO, CY, EL), 18 students (HR)  - 6 teachers (RO, CY, EL), 6 teachers (HR)  - parents, members of school administration  The budget approved for each partner | Croatia | April 2024 | Agenda, posts on the project digital web platform, 1 questionnaire of feedback from students;online questionnaires to assess meeting quality for students (1) and teachers (1); 3 thematic workshops;  3 teaching units for 3 digital learning activities for students on *Arts and ICT*;  1 plan for the activity on the topic of sustainable development;  4 new digital apps used (one per partner).  -Raised digital competencies of students and teachers.  -Developing English communication and social skills. | 18 Europass certificates, 36 certificates of participation for students and 12 for teachers; 1 list of participants of the activities, 1 meeting report; number of respondens (students and teachers) with positive feedback; new posts on project platform (3 teaching units, 1 plan for sustainable activity, 4 tutorials for digital apps used) and on eTwinning page (photos). |
| Short-term exchange for group of students – teaching and learning activities in *Health Education and Languages* | WP2 | - 18 students (RO, EL, HR), 18 students (CY)  - 6 teachers (RO, EL, HR), 6 teachers (CY)  - parents, members of school administration  The budget approved for each partner | Cyprus | Oct. – Nov. 2024 | Agenda, posts on the project digital web platform, 1 questionnaire of feedback from students;online questionnaires to assess meeting quality for students (1) and teachers (1); 3 thematic workshops;  3 teaching units for 3 digital learning activities for students in *Health Education and Languages* ;  1 plan for the activity on the topic of sustainable development;  4 new digital apps used (one per partner).  -Raised digital competencies of students and teachers.  -Developing English communication and social skills. | 18 Europass certificates, 36 certificates of participation for students and 12 for teachers; 1 list of participants of the activities, 1 meeting report; number of respondens (students and teachers) with positive feedback; new posts on project platform (3 teaching units, 1 plan for sustainable activity, 4 tutorials for digital apps used) and on eTwinning page (photos). |
| O1, O2, O3  Short-term exchange for group of students – teaching and learning activities in *Humanistic subjects* | WP2 | - 18 students (RO, CY, HR), 18 students (EL)  - 6 teachers (RO, CY, HR), 6 teachers (EL)  - parents, members of school administration  The budget approved for each partner | Greece | February 2025 | Agenda, posts on the project digital web platform, 1 questionnaire of feedback from students;online questionnaires to assess meeting quality for students (1) and teachers (1); 3 thematic workshops;  3 teaching units for 3 digital learning activities for students in *Humanistic subjects*;  1 plan for the activity on the topic of sustainable development;  4 new digital apps used (one per partner).  -Raised digital competencies of students and teachers.  -Developing English communication and social skills. | 18 Europass certificates, 36 certificates of participation for students and 12 for teachers; 1 list of participants of the activities, 1 meeting report; number of respondens (students and teachers) with positive feedback; new posts on project platform (3 teaching units, 1 plan for sustainable activity, 4 tutorials for digital apps used) and on eTwinning page (photos). |
| O1, O2, O3  Short-term exchange for group of students – teaching and learning activities in *Sciences* | WP2 | - 18 students (EL, CY, HR), 18 students (RO)  - 6 teachers (EL, CY, HR), 6 teachers (RO)  - parents, members of school administration  The budget approved for each partner | Romania | May 2025 | Agenda, posts on the project digital web platform, 1 questionnaire of feedback from students;online questionnaires to assess meeting quality for students (1) and teachers (1); 3 thematic workshops;  3 teaching units for 3 digital learning activities for students in *Sciences*;  1 plan for the activity on the topic of sustainable development;  4 new digital apps (one per partner).  - Raised digital competencies of students and teachers.  -Developing English communication and social skills. | 18 Europass certificates, 36 certificates of participation for students and 12 for teachers; 1 list of participants of the activities, 1 meeting report; number of respondens (students and teachers) with positive feedback; new posts on project platform (3 teaching units, 1 plan for sustainable activity, 4 tutorials for digital apps used) and on eTwinning page (photos). |
| **O1, O2, O3** | **WP3** | **1200 euros** |  |  |  |  |
| Designing the digital web platform of the project | WP3 | manegement team from Croatia  1000 euro | Croatia | Oct. 2023 – January 2024 | The digital web platform | - number of visitors per month;  - number of digital materials posted |
| Designing the page of  the project on eTwining platform | WP3 | manegement team from Greece | Greece | October 2023 – January 2024 | The page of the project on eTwining platform | - number of posts |
| Virtual competition for voting the project LOGO (created by students) | WP3 | manegement team from Romania  200 euro | Romania | 20 December 2023 | - minimum 10 logos created per partner  - 200 badges with the project logo distributed to students involved (creating and voting logos – 50 students per partner) | -an attractive logo that contains elements specific to the project voted by a large number of students |
| Virtual workshop for student learning activities in *Arts and ICT* | WP3 | SC  100 students from partner schools  - teachers members in the implementation teams in partner schools | Croatia | May 2024 | - agenda of workshop and the report after;  -created teaching unit with the use of digital tools *in Arts and ICT* (*tutorial about* how to use a digital tool*, an exemple* created by teachers from host school);  - raised digital competencies and personal skills of students and teachers;  -increasing the number of students involved in the project;  -increasing the coolaboration between partner schools;  - posts on the eTwinning page and digital project platform; | - printscreens with participants at the workshop;  - implementing during classes in partner schools (*list with number of teachers and students who used this unit/digital tools*);  -number of digital resources posted on digital platform after the virtual workshop (*minimum one per partner*);  -1questionnaire for evaluating the quality of the activities carried out in the virtual workshops and 1 evaluation report produced; |
| Virtual workshop for student learning activities in *Health Education and Languages* | WP3 | SC  100 students from partner schools  - teachers members in the implementation teams in partner schools | Cyprus | Nov. 2024 | - agenda of workshop and the report after;  -created teaching unit with the use of digital tools *Health Education and Languages* (*tutorial about* how to use a digital tool*, an exemple* created by teachers from host school);  - raised digital competencies and personal skills of students and teachers;  -increasing the number of students involved in the project;  -increasing the coolaboration between partner schools;  - posts on the eTwinning page and digital project platform; | - printscreens with participants at the workshop;  - implementing during classes in partner schools (*list with number of teachers and students who used this unit/digital tools*);  -number of digital resources posted on digital platform after the virtual workshop (*minimum one per partner*);  -1questionnaire for evaluating the quality of the activities carried out in the virtual workshops and 1 evaluation report produced; |
| Virtual workshop for student learning activities in *Humanistic subjects* | WP3 | SC  100 students from partner schools  - teachers members in the implementation teams in partner schools | Greece | March 2025 | - agenda of workshop and the report after;  -created teaching unit with the use of digital tools *Humanistic subjects* (*tutorial about* how to use a digital tool*, an exemple* created by teachers from host school);  - raised digital competencies and personal skills of students and teachers;  -increasing the number of students involved in the project;  -increasing the coolaboration between partner schools;  - posts on the eTwinning page and digital project platform; | - printscreens with participants at the workshop;  - implementing during classes in partner schools (*list with number of teachers and students who used this unit/digital tools*);  -number of digital resources posted on digital platform after the virtual workshop (*minimum one per partner*);  -1questionnaire for evaluating the quality of the activities carried out in the virtual workshops and 1 evaluation report produced; |
| Virtual workshop for student learning activities in *Sciences* | WP3 | SC  100 students from partner schools  - teachers members in the implementation teams in partner schools | Romania | June 2025 | - agenda of workshop and the report after;  -created teaching unit with the use of digital tools in *Sciences* (*tutorial about* how to use a digital tool*, an exemple* created by teachers from host school);  - raised digital competencies and personal skills of students and teachers;  -increasing the number of students involved in the project;  -increasing the coolaboration between partner schools;  - posts on the eTwinning page and digital project platform; | - printscreens with participants at the workshop;  - implementing during classes in partner schools (*list with number of teachers and students who used this unit/digital tools*);  -number of digital resources posted on digital platform after the virtual workshop (*minimum one per partner*);  -1questionnaire for evaluating the quality of the activities carried out in the virtual workshops and 1 evaluation report produced; |
| **O1, O2** | **WP4** | **10080 euro** |  |  |  |  |
| Joint teacher training event | WP4 | - 6 teachers from RO, EL, HR  - 2 teachers from CY  - management team from Cyprus  - 8370 Euros | Cyprus | 6-10 Nov. 2023 | -Agenda and the training program realized;  -6 Europass teachers certificates completed;  -8 certificates of participation at the training;  - list of participants;  - the detailed project implementation plan finished;  -developing teachers' digital skills and competences;  -developing cooperation, communication and working skills in an international group. | -1questionnaire to assess the quality of the joint teacher training and 1 report produced;  -observing the teachers’s satisfaction in training activities;  - number of digital applications learnt during the training;  - assuming the responsibilities specified in the application form and in the partnership agreements. |
| Virtual workshop for  teachers in using the digital web platform of the project | WP4 | 20 project members teams;  32 participating teachers from partners schools;  310 euros | Croatia | January 2024 | Tutorial for using the platform;  - increase the capacity of teachers for using platform and upload materials produced | 1 tutorial; list of participants; printscreens during the virtual workshop; |
| Virtual workshop for teachers - application digital tools and apps in *Arts and ICT* | WP4 | 25 teachers from partner schools;  350 euros | Croatia | February 2024 | Agenda and the content of the virtual training;  - tutorial of 2 new digital applications to be used in classes;  - improving the digital teaching skills;  -1questionnaire for evaluating the quality of the activities carried out in the virtual workshop; | Printscreens will be made as evidence of the workshop; list of participants;  the certificates of participation in virtual workshop for teachers;  -enriching the digital skills of teachers by creating innovative digital materials;  - 1 evaluation report produced; |
| Virtual workshop for teachers - application digital tools and apps in *Health education and Languages* | WP4 | 25 teachers from partner schools;  350 euros | Cyprus | June 2024 | Agenda and the content of the virtual training;  - tutorial of 2 new digital applications to be used in classes;  - improving the digital teaching skills;  -1questionnaire for evaluating the quality of the activities carried out in the virtual workshop; | Printscreens will be made as evidence of the workshop; list of participants;  the certificates of participation in virtual workshop for teachers;  -enriching the digital skills of teachers by creating innovative digital materials;  - 1 evaluation report produced; |
| Virtual workshop for teachers - application digital tools and apps in *Humanistic subjects* | WP4 | 25 teachers from partner schools;  350 euros | Greece | December 2024 | Agenda and the content of the virtual training;  - tutorial of 2 new digital applications to be used in classes;  - improving the digital teaching skills;  -1questionnaire for evaluating the quality of the activities carried out in the virtual workshop; | Printscreens will be made as evidence of the workshop; list of participants;  the certificates of participation in virtual workshop for teachers;  -enriching the digital skills of teachers by creating innovative digital materials;  - 1 evaluation report produced; |
| Virtual workshop for teachers - application digital tools and apps in *Sciences* | WP4 | 25 teachers from partner schools;  350 euros | Romania | April 2025 | Agenda and the content of the virtual training;  - tutorial of 2 new digital applications to be used in classes;  - improving the digital teaching skills;  -1questionnaire for evaluating the quality of the activities carried out in the virtual workshop; | Printscreens will be made as evidence of the workshop; list of participants;  the certificates of participation in virtual workshop for teachers;  -enriching the digital skills of teachers by creating innovative digital materials;  - 1 evaluation report produced; |
| **O1, O2, O3** | **WP5** | **0 euros** |  |  |  |  |
| Dissemination & exploitation of the project results Plan | WP5 | SC  - the persons responsible for the dissemination activity @ the exploitation of the project results from the management team in each school | Cyprus | Dec. 2023 | 1 plan for disemination and exploitation of the project results | -two dissemination progress reports; |
| Development of the project’s Visual Identity: creat project logo and use the EU visual identity | WP5 | SC | Romania | Dec. 2023 | - using the elements of visual identity on all documents related with the project |  |
| Dissemination the project results on digital web platform of the project | WP5 | SC  - members of project management teams;  - 650 students, 100 teachers from partner schools, 100 other stakeholders | Croatia | Oct.2023 – sept.2025 | 1 digital platform of the project; the platform will function as a collaborative space for partners and other stakeholders. | Number of visitors – 1000;  - number of digital innovative didactic materials posted by students and teachers; |
| Development of the eTwinning page of the project | WP5 | SC  members of project management teams | Greece | Oct.2023 – sept.2025 | 1 eTwinning page | Number of visitors – 1000;  -at least 5 posts per year presenting the project’s progress |
| Meetings with teachers and students for the transfer of information regarding the project | WP5 | SC, teachers, students, parents, local representatives | SC | After each mobility with physical participation | - presentation of the digital applications used and the materials created. | Lists of presence; |
| Organisating a ***social media campagn***:  - Visibility of the project on each school’s official website and social media (FB pages of schools);  - Creation of at least 15 short interviews from each partner school;  - all partners will present the Project at local, national and european level by attending educational conferences/meetings. | WP | SC, members of project management teams;  - students, teachers, parents, teachers from other schools, educational representative | Greece | Oct.2023 – sept.2025 | - presentation the progress of the project and the results obtained;  - promoting the project and the skills acquired by participating in the activities;  - promoting the project at local/bational / international level (colect evidence and send to the google drive). | - 5 FB posts per year/country;  -two articles posted on the schools’ website or FB pages of schools;  - 4 newsletters (one per school);  -interviews with 5 teachers and 10 students /per school posted on eTwinning page /FB pages of schools. |
| Organisation meetings with teachers from the regional educational community | WP5 | SC  - members of project management teams  - teachers from other schools (at least 20 participants) | Romania | Oct.2023 – sept.2025 | - promoting the project through all stages of implementation;  -positive feedback from teachers outside the consortium exploiting the material in their class. | -programme, online invitation, google form for registrations, list of participants;  - each partner hold 2 such meetings, one per year, make dissemination reports; |
| Organisation of two online conferences | WP5 | - 100 participants: 20 students and 20 teachers from each scool members of project teams, 20 teachers from other schools from community, 4 representative of the parents council, 10 representatives of local community, 12 members of school boards, 14 parents; | Cyprus | Oct.2023 – sept.2025 | - the programme, online invitations;  -securing project’s sustainability through the establishment of collaborations with local authorities and other schools | Programme/ agenda, online invitations, prinscreens during conferences, reports produced; |

***Steering Committee*** (SC) - **project coordinators**

1. Daniela Crizantema Nane (Romania) Scoala Gimnaziala "Constantin Parfene"
2. Josephine Pavlou Angelide (Cyprus) Perifereiako Gymnasio Akakiou
3. Josip Beštek (Croatia) Osnovna skola Novi Marof
4. Vasiliki Papaioannou (Greece) 1st Gymnasium of Byron